## 01_SYSTEM_SETTINGS
DYNASTY ACCOUNTING OS v1.0 — SYSTEM SETTINGS
Setting | Value | Notes
Company Name | Shylow Thompson LLC
Primary Entity | Shylow Thompson LLC
Fiscal Year Start | 01/01/2026
Fiscal Year End | 12/31/2026
Accounting Method | Accrual | GAAP standard
Base Currency | USD
Version | 1.0
Build Date | 05/29/2026
Next Review | 12/31/2026
Tax ID | [ENTER EIN] | Federal EIN
State | Missouri
Chart of Accounts Version | RE-COA-2026

## 02_USERS_ROLES
DYNASTY ACCOUNTING OS — USERS & ROLES
User_ID | Full_Name | Role | Entity_Access | Permissions | Last_Login | Status | Notes
U001 | Shylow Thompson | CEO / Owner | All Entities | Full Access | 05/29/2026 | Active | Primary user
U002 | Accountant | Controller | Shylow Thompson LLC | Read/Write |  | Active
U003 | Investor | Investor Portal | Assigned Deals Only | Read Only |  | Active

## 03_AUDIT_LOG
DYNASTY ACCOUNTING OS — AUDIT LOG
Log_ID | Timestamp | User_ID | User_Name | Sheet_Modified | Cell_Reference | Old_Value | New_Value | Action_Type | Notes
AL001 | 05/29/2026 09:00 | U001 | Shylow Thompson | 01_SYSTEM_SETTINGS | B4 |  | Shylow Thompson LLC | INITIALIZE | System initialization
AL002 | 05/29/2026 09:01 | U001 | Shylow Thompson | 50_PROPERTY_MASTER | B4 |  | 502 Buckley | CREATE | Added 502 Buckley property

## 04_ENTITY_MANAGER
DYNASTY ACCOUNTING OS — ENTITY MANAGER
Entity_ID | Entity_Name | Entity_Type | EIN | State | Formation_Date | Primary_Contact | Role | Status | Notes
E001 | Shylow Thompson LLC | Operating LLC | [EIN] | Missouri |  | Shylow Thompson | CEO | Active | Primary operating entity
E002 | Dynasty OS | Tech/SaaS LLC | [EIN] | Missouri |  | Shylow Thompson | CEO | Active | Software operations
E003 | KhakiSol | Brand/Creative LLC | [EIN] | Missouri |  | Shylow Thompson | CEO | Active | Creative & brand
E004 | 502 Buckley LLC | Property LLC | [EIN] | Missouri |  | Shylow Thompson | Manager | Active | Property holding entity

## 05_DASHBOARD_HOME
DYNASTY ACCOUNTING OS — COMMAND CENTER
QUICK NAVIGATION
Section | Sheet Name | Description | Tab Color
SYSTEM | 01_SYSTEM_SETTINGS | Global configuration | Dark Gray
SYSTEM | 02_USERS_ROLES | User access management | Dark Gray
SYSTEM | 03_AUDIT_LOG | Change history | Dark Gray
SYSTEM | 04_ENTITY_MANAGER | Business entities | Dark Gray
SYSTEM | 05_DASHBOARD_HOME | This navigation screen | Dark Gray
ACCOUNTING | 10_CHART_OF_ACCOUNTS | Full COA 1000-6999 | Dark Blue
ACCOUNTING | 11_JOURNAL_ENTRIES | Double-entry transactions | Dark Blue
ACCOUNTING | 12_GENERAL_LEDGER | Account activity detail | Dark Blue
ACCOUNTING | 13_TRIAL_BALANCE | Debit/credit balance check | Dark Blue
ACCOUNTING | 14_BALANCE_SHEET | Assets = Liabilities + Equity | Dark Blue
ACCOUNTING | 15_INCOME_STATEMENT | Revenue - Expenses = Net Income | Dark Blue
ACCOUNTING | 16_CASH_FLOW | Operating/Investing/Financing | Dark Blue
ACCOUNTING | 17_BUDGETS | Monthly budget by account | Dark Blue
ACCOUNTING | 18_BUDGET_VS_ACTUAL | Variance analysis | Dark Blue
BANKING | 20_BANK_ACCOUNTS | Account registry | Teal
BANKING | 21_BANK_TRANSACTIONS | Transaction feed | Teal
BANKING | 22_RECONCILIATION | Bank rec | Teal
BANKING | 23_CREDIT_CARDS | Card transactions | Teal
AR/AP | 30_CUSTOMERS | Customer database | Orange
AR/AP | 31_INVOICES | Invoice management | Orange
AR/AP | 32_RECEIVABLES | AR tracking | Orange
AR/AP | 33_AGING_REPORT | AR aging buckets | Orange
AR/AP | 40_VENDORS | Vendor database | Orange
AR/AP | 41_BILLS | Bill management | Orange
AR/AP | 42_PAYABLES | AP tracking | Orange
AR/AP | 43_AGING_PAYABLES | AP aging buckets | Orange
REAL ESTATE | 50_PROPERTY_MASTER | Property portfolio | Green
REAL ESTATE | 51_ACQUISITIONS | Deal pipeline | Green
REAL ESTATE | 52_REHAB_ENGINE | 502 Buckley rehab tracker | Green
REAL ESTATE | 53_DRAWS | Construction draws | Green
REAL ESTATE | 54_HOLDING_COSTS | Monthly holding | Green
REAL ESTATE | 55_RENTS | Rent roll | Green
REAL ESTATE | 56_CAPEX | Capital expenditures | Green
REAL ESTATE | 57_DISPOSITIONS | Property sales | Green
DEAL ANALYZER | 60_WHOLESALE_ANALYZER | Wholesale calculator | Purple
DEAL ANALYZER | 61_FLIP_ANALYZER | Fix & flip calculator | Purple
DEAL ANALYZER | 62_BRRR_ANALYZER | BRRR calculator | Purple
DEAL ANALYZER | 63_DEVELOPMENT_ANALYZER | Ground-up development | Purple
DEAL ANALYZER | 64_LAND_ANALYZER | Land deal calculator | Purple
INVESTORS | 70_INVESTORS | Investor registry | Dark Red
INVESTORS | 71_CAPITAL_STACK | Capital structure | Dark Red
INVESTORS | 72_WATERFALL | Distribution waterfall | Dark Red
INVESTORS | 73_DISTRIBUTIONS | Distribution history | Dark Red
INVESTORS | 74_INVESTOR_REPORTS | Investor summaries | Dark Red
AI | 80_AI_DEAL_SCORING | Deal scoring engine | Light Blue
AI | 81_AI_FORECASTING | 13-week cash forecast | Light Blue
AI | 82_AI_ANOMALIES | Expense anomaly detection | Light Blue
AI | 83_AI_ASSISTANT | Trooper Accountant AI | Light Blue
EXECUTIVE | 90_KPI_DASHBOARD | CEO cockpit metrics | Gold
EXECUTIVE | 91_CASH_FORECAST | 12-month cash projection | Gold
EXECUTIVE | 92_NET_WORTH_TRACKER | Net worth history | Gold
EXECUTIVE | 93_PORTFOLIO_ANALYTICS | Portfolio performance | Gold
EXECUTIVE | 94_EXECUTIVE_REPORT | Executive summary report | Gold
SYSTEM STATUS
Metric | Value | Status
Last Updated | 05/29/2026 | Current
Formula Errors | 0 | OK
Accounting Balance | Balanced | OK
Active Properties | 1 | Active
Active Deals | 1 | Active
Version | 1.0 | Current

## 10_CHART_OF_ACCOUNTS
CHART OF ACCOUNTS — Dynasty Accounting OS v1.0
Account_Number | Account_Name | Account_Type | Sub_Type | Normal_Balance | Description | Active | Entity
1000 | Cash — Operating Account | Asset | Current Asset | Debit | Primary operating checking | Yes | All
1010 | Cash — Savings Account | Asset | Current Asset | Debit | Business savings | Yes | All
1020 | Cash — Reserve Fund | Asset | Current Asset | Debit | Capital reserves | Yes | All
1030 | Cash — Tax Reserve | Asset | Current Asset | Debit | Tax payment reserves | Yes | All
1040 | Petty Cash | Asset | Current Asset | Debit | Small cash purchases | Yes | All
1100 | Accounts Receivable | Asset | Current Asset | Debit | Money owed to company | Yes | All
1110 | AR — Assignment Fees | Asset | Current Asset | Debit | Wholesale assignment receivables | Yes | All
1120 | AR — Rental Income | Asset | Current Asset | Debit | Rent receivables | Yes | All
1200 | Prepaid Expenses | Asset | Current Asset | Debit | Prepaid insurance, rent | Yes | All
1210 | Prepaid Insurance | Asset | Current Asset | Debit |  | Yes | All
1300 | Inventory — Land | Asset | Real Estate Inventory | Debit | Land held for sale | Yes | All
1310 | Inventory — Wholesale Contracts | Asset | Real Estate Inventory | Debit | Contracts under assignment | Yes | All
1400 | Real Estate — Investment Properties | Asset | Fixed Asset | Debit | Properties held for investment | Yes | All
1410 | 502 Buckley — Building | Asset | Fixed Asset | Debit | Building value at purchase | Yes | STLLC
1420 | 502 Buckley — Land | Asset | Fixed Asset | Debit | Land value at purchase | Yes | STLLC
1430 | Accumulated Depreciation — Buildings | Asset | Fixed Asset | Credit | Contra asset | Yes | All
1500 | Equipment | Asset | Fixed Asset | Debit | Tools, equipment | Yes | All
1510 | Vehicles | Asset | Fixed Asset | Debit | Company vehicles | Yes | All
1520 | Accumulated Depreciation — Equipment | Asset | Fixed Asset | Credit | Contra asset | Yes | All
1600 | Security Deposits Held | Asset | Other Asset | Debit | Tenant deposits | Yes | All
1700 | Due from Related Entities | Asset | Other Asset | Debit | Inter-company receivables | Yes | All
1800 | Investments — Joint Ventures | Asset | Other Asset | Debit | JV investment interests | Yes | All
1900 | Other Assets | Asset | Other Asset | Debit | Miscellaneous | Yes | All
2000 | Accounts Payable | Liability | Current Liability | Credit | Vendor bills owed | Yes | All
2010 | AP — Contractors | Liability | Current Liability | Credit | Contractor invoices | Yes | All
2020 | AP — Materials | Liability | Current Liability | Credit | Material supplier invoices | Yes | All
2100 | Credit Cards Payable | Liability | Current Liability | Credit | Credit card balances | Yes | All
2110 | Chase Business Card | Liability | Current Liability | Credit |  | Yes | All
2200 | Accrued Expenses | Liability | Current Liability | Credit | Expenses incurred not yet paid | Yes | All
2210 | Accrued Interest | Liability | Current Liability | Credit |  | Yes | All
2220 | Accrued Payroll | Liability | Current Liability | Credit |  | Yes | All
2300 | Security Deposits — Tenant | Liability | Current Liability | Credit | Deposits held for tenants | Yes | All
2400 | Short-Term Debt | Liability | Current Liability | Credit | Debt due within 12 months | Yes | All
2500 | Mortgage Payable — 502 Buckley | Liability | Long-Term Liability | Credit | FHA mortgage principal | Yes | STLLC
2510 | Hard Money Loans | Liability | Long-Term Liability | Credit | Hard money borrowings | Yes | All
2520 | Private Lender Notes | Liability | Long-Term Liability | Credit | Private money loans | Yes | All
2530 | Seller Financing | Liability | Long-Term Liability | Credit | Owner carry notes | Yes | All
2600 | Deferred Revenue | Liability | Long-Term Liability | Credit | Advance rent payments | Yes | All
2700 | Due to Related Entities | Liability | Long-Term Liability | Credit | Inter-company payables | Yes | All
2800 | Tax Payable — Income | Liability | Current Liability | Credit | Estimated income taxes | Yes | All
2810 | Tax Payable — Sales | Liability | Current Liability | Credit | Sales tax collected | Yes | All
2900 | Other Liabilities | Liability | Other Liability | Credit | Miscellaneous | Yes | All
3000 | Members Equity — Shylow Thompson | Equity | Owners Equity | Credit | Primary member equity | Yes | All
3010 | Retained Earnings | Equity | Retained Earnings | Credit | Accumulated profits | Yes | All
3020 | Members Draws | Equity | Owners Equity | Debit | Owner distributions | Yes | All
3030 | Capital Contributions | Equity | Owners Equity | Credit | Cash invested by owner | Yes | All
3100 | Investor Capital — Preferred | Equity | Investor Equity | Credit | Preferred equity investors | Yes | All
3110 | Investor Capital — Common | Equity | Investor Equity | Credit | Common equity investors | Yes | All
3200 | Profit Distributions | Equity | Distributions | Debit | Investor profit distributions | Yes | All
4000 | Wholesale Assignment Fees | Revenue | Operating Revenue | Credit | Assignment contract fees | Yes | All
4010 | Flip Profits | Revenue | Operating Revenue | Credit | Net profit from flips | Yes | All
4020 | Rental Income — Residential | Revenue | Operating Revenue | Credit | Residential rents | Yes | All
4030 | Rental Income — Commercial | Revenue | Operating Revenue | Credit | Commercial rents | Yes | All
4040 | Late Fees | Revenue | Operating Revenue | Credit | Tenant late fees | Yes | All
4050 | Application Fees | Revenue | Operating Revenue | Credit | Rental application fees | Yes | All
4100 | Consulting Income | Revenue | Other Revenue | Credit | Advisory/consulting fees | Yes | All
4110 | Dynasty OS Revenue | Revenue | Other Revenue | Credit | SaaS/software revenue | Yes | Dynasty OS
4120 | KhakiSol Revenue | Revenue | Other Revenue | Credit | Creative/brand revenue | Yes | KhakiSol
4200 | Interest Income | Revenue | Other Revenue | Credit | Bank and investment interest | Yes | All
4300 | Gain on Sale — Real Estate | Revenue | Other Revenue | Credit | Profit from property sales | Yes | All
4400 | Other Income | Revenue | Other Revenue | Credit | Miscellaneous income | Yes | All
5000 | Cost of Properties Sold | COGS | Direct Cost | Debit | Book value of sold properties | Yes | All
5010 | Acquisition Costs | COGS | Direct Cost | Debit | Purchase price + closing costs | Yes | All
5100 | Rehab — Labor | COGS | Direct Cost | Debit | Contractor labor | Yes | All
5110 | Rehab — Materials | COGS | Direct Cost | Debit | Materials and supplies | Yes | All
5120 | Rehab — Permits | COGS | Direct Cost | Debit | Building permits | Yes | All
5130 | Rehab — Subcontractors | COGS | Direct Cost | Debit | Specialty contractors | Yes | All
5200 | Holding Costs | COGS | Direct Cost | Debit | While under rehab/sale | Yes | All
5210 | Holding — Mortgage Interest | COGS | Direct Cost | Debit | Interest during hold | Yes | All
5220 | Holding — Insurance | COGS | Direct Cost | Debit | Property insurance | Yes | All
5230 | Holding — Utilities | COGS | Direct Cost | Debit | Utilities during hold | Yes | All
5240 | Holding — Property Tax | COGS | Direct Cost | Debit | Taxes during hold | Yes | All
5300 | Assignment Costs | COGS | Direct Cost | Debit | Marketing, finding fees | Yes | All
5400 | Development Costs | COGS | Direct Cost | Debit | Ground-up development | Yes | All
6000 | Salaries & Wages | Expense | Operating Expense | Debit | Payroll | Yes | All
6010 | Contract Labor | Expense | Operating Expense | Debit | 1099 workers | Yes | All
6100 | Marketing — Digital | Expense | Operating Expense | Debit | Online ads, PPC | Yes | All
6110 | Marketing — Direct Mail | Expense | Operating Expense | Debit | Mailers, postcards | Yes | All
6120 | Marketing — Software (PropWire/DealMachine) | Expense | Operating Expense | Debit | Lead gen tools | Yes | All
6130 | Marketing — Cold Calling | Expense | Operating Expense | Debit | Dialers, call centers | Yes | All
6200 | Office Expenses | Expense | Operating Expense | Debit | Supplies, equipment | Yes | All
6210 | Rent / Lease | Expense | Operating Expense | Debit | Office space | Yes | All
6220 | Utilities — Office | Expense | Operating Expense | Debit | Electric, internet | Yes | All
6300 | Professional Fees — Legal | Expense | Operating Expense | Debit | Attorney fees | Yes | All
6310 | Professional Fees — Accounting | Expense | Operating Expense | Debit | CPA/bookkeeper | Yes | All
6320 | Professional Fees — Consulting | Expense | Operating Expense | Debit | Advisors | Yes | All
6400 | Software & Technology | Expense | Operating Expense | Debit | Subscriptions | Yes | All
6410 | Dynasty OS Development | Expense | Operating Expense | Debit | App/web development | Yes | Dynasty OS
6500 | Insurance | Expense | Operating Expense | Debit | Business insurance | Yes | All
6510 | E&O Insurance | Expense | Operating Expense | Debit | Errors & Omissions | Yes | All
6600 | Vehicle & Travel | Expense | Operating Expense | Debit | Car, mileage, travel | Yes | All
6610 | Fuel | Expense | Operating Expense | Debit | Gas expenses | Yes | All
6700 | Bank Fees | Expense | Operating Expense | Debit | Account fees, wire fees | Yes | All
6800 | Interest Expense | Expense | Operating Expense | Debit | Loan interest | Yes | All
6810 | Mortgage Interest — 502 Buckley | Expense | Operating Expense | Debit | FHA mortgage interest | Yes | STLLC
6900 | Depreciation Expense | Expense | Operating Expense | Debit | Annual depreciation | Yes | All
6910 | Depreciation — 502 Buckley | Expense | Operating Expense | Debit |  | Yes | STLLC
6990 | Miscellaneous Expenses | Expense | Operating Expense | Debit | Other expenses | Yes | All

## 11_JOURNAL_ENTRIES
JOURNAL ENTRIES — Double-Entry Accounting Ledger
JE_ID | Date | Description | Debit_Acct | Debit_Name | Debit_Amt | Credit_Acct | Credit_Name | Credit_Amt | Entity | Reference | Posted | Notes
JE001 | 05/01/2026 | Opening Capital Contribution | 1000 | Cash — Operating Account | 25000 | 3030 | Capital Contributions | 25000 | STLLC | OPENING | Yes | Initial capital
JE002 | 05/01/2026 | Purchase 502 Buckley — Building | 1410 | 502 Buckley — Building | 97900 | 2500 | Mortgage Payable — 502 Buckley | 114000 | STLLC | CLOSING-502 | Yes | FHA purchase close
JE003 | 05/01/2026 | Purchase 502 Buckley — Land | 1420 | 502 Buckley — Land | 16100 | 1000 | Cash — Operating Account | 4500 | STLLC | CLOSING-502 | Yes | Land allocation + closing costs
JE004 | 05/01/2026 | Acquisition Closing Costs | 5010 | Acquisition Costs | 4500 | 1000 | Cash — Operating Account | 0 | STLLC | CLOSING-502 | Yes | Included in JE003 credit
JE005 | 05/15/2026 | Rehab Materials — Demo Phase | 5110 | Rehab — Materials | 3500 | 1000 | Cash — Operating Account | 3500 | STLLC | INV-001 | Yes | Demo phase materials
JE006 | 05/20/2026 | Rehab Labor — Contractor Draw 1 | 5100 | Rehab — Labor | 8000 | 2010 | AP — Contractors | 8000 | STLLC | INV-002 | Yes | First labor draw
JE007 | 05/25/2026 | PropWire Subscription | 6120 | Marketing — Software | 299 | 2110 | Chase Business Card | 299 | STLLC | CC-001 | Yes | Monthly subscription
BALANCE CHECK (Posted): |  |  |  | Total Debits: | 155299 |  | Total Credits: | 155299
|  |  |  | Difference (must = 0): | 0

## 12_GENERAL_LEDGER
GENERAL LEDGER — Account Activity Detail
Select Account Number: |  | 1000
GL_ID | Date | Account_Number | Account_Name | Description | JE_Reference | Debit | Credit | Entity
GL-001 | 05/01/2026 | 1000 | Cash — Operating Account | Opening capital contribution | JE001 | 25000 | 0 | STLLC

## 13_TRIAL_BALANCE
TRIAL BALANCE — As of 05/29/2026
Account_Number | Account_Name | Account_Type | Debit | Credit
1000 | Cash — Operating Account | Asset | 25000 | 0
1410 | 502 Buckley — Building | Asset | 97900 | 0
1420 | 502 Buckley — Land | Asset | 16100 | 0
2010 | AP — Contractors | Liability | 0 | 0
2110 | Chase Business Card | Liability | 0 | 0
2500 | Mortgage Payable — 502 Buckley | Liability | 0 | 0
3030 | Capital Contributions | Equity | 0 | 0
5010 | Acquisition Costs | COGS | 4500 | 0
5100 | Rehab — Labor | COGS | 8000 | 0
5110 | Rehab — Materials | COGS | 3500 | 0
6120 | Marketing — Software | Expense | 299 | 0
TOTAL |  |  | 155299 | 0
DIFFERENCE (must = 0) |  |  | 155299

## 14_BALANCE_SHEET
BALANCE SHEET — As of 05/29/2026
ASSETS
CURRENT ASSETS
Cash — Operating Account |  | 17200
Accounts Receivable |  | 0
Prepaid Expenses |  | 0
| Total Current Assets | 17200
FIXED ASSETS
502 Buckley — Building |  | 97900
502 Buckley — Land |  | 16100
Accumulated Depreciation |  | 0
| Total Fixed Assets | 114000
TOTAL ASSETS |  | 131200
LIABILITIES & EQUITY
CURRENT LIABILITIES
AP — Contractors |  | 8000
Chase Business Card |  | 299
Accrued Expenses |  | 0
| Total Current Liabilities | 8299
LONG-TERM LIABILITIES
Mortgage Payable — 502 Buckley |  | 114000
| Total Long-Term Liabilities | 114000
TOTAL LIABILITIES |  | 0
OWNER'S EQUITY
Capital Contributions |  | 25000
Members Draws |  | 0
Retained Earnings |  | -8799
| Total Owner's Equity | 16201
TOTAL LIABILITIES + EQUITY |  | -8799
BALANCE CHECK (must = $0): |  | 139999

## 15_INCOME_STATEMENT
INCOME STATEMENT — Period: Jan 2026 — May 2026
REVENUE
Wholesale Assignment Fees |  | 0
Flip Profits |  | 0
Rental Income |  | 0
Other Revenue |  | 0
| TOTAL REVENUE | 0
COST OF GOODS SOLD (COGS)
Acquisition Costs |  | 4500
Rehab — Labor |  | 8000
Rehab — Materials |  | 3500
Holding Costs |  | 1080
Assignment Costs |  | 0
| TOTAL COGS | 17080
| GROSS PROFIT | -17080
| Gross Margin % | 0%
OPERATING EXPENSES
Marketing |  | 299
Professional Fees |  | 0
Software & Technology |  | 0
Insurance |  | 0
Vehicle & Travel |  | 0
Bank Fees |  | 0
Other Expenses |  | 0
| TOTAL OPERATING EXPENSES | 299
| OPERATING INCOME (EBIT) | -17379
BELOW-THE-LINE
Interest Expense |  | 0
Depreciation |  | 0
| NET INCOME | -17379

## 16_CASH_FLOW
CASH FLOW STATEMENT — YTD 2026
A. OPERATING ACTIVITIES
Net Income |  | -16379
Add: Depreciation |  | 0
Changes in Accounts Receivable |  | 0
Changes in Accounts Payable |  | 8299
| Net Operating Cash Flow | -8080
B. INVESTING ACTIVITIES
Property Acquisitions |  | -114000
Rehab Spending |  | -11500
Proceeds from Property Sales |  | 0
| Net Investing Cash Flow | -125500
C. FINANCING ACTIVITIES
Mortgage Proceeds |  | 114000
Mortgage Payments |  | 0
Capital Contributions |  | 25000
Owner Draws |  | 0
| Net Financing Cash Flow | 139000
NET CHANGE IN CASH |  | 5420
Beginning Cash Balance |  | 0
ENDING CASH BALANCE |  | 5420

## 17_BUDGETS
ANNUAL BUDGET — FY 2026
Account_Number | Account_Name | Category | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Annual_Total
4000 | Wholesale Assignment Fees | Revenue | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 60000
4020 | Rental Income | Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5100 | Rehab — Labor | COGS | 8000 | 8000 | 5000 | 3000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26000
5110 | Rehab — Materials | COGS | 5000 | 5000 | 3000 | 2000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000
5210 | Holding — Mortgage | COGS | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 9000
5220 | Holding — Insurance | COGS | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1200
6100 | Marketing — Digital | Expense | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 18000
6120 | Marketing — Software | Expense | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 299 | 3588
6300 | Professional Fees — Legal | Expense | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 500 | 0 | 3000
6310 | Professional Fees — Accounting | Expense | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000
6400 | Software & Technology | Expense | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 2400
6500 | Insurance | Expense | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800
6600 | Vehicle & Travel | Expense | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 3600
6700 | Bank Fees | Expense | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 300

## 18_BUDGET_VS_ACTUAL
BUDGET VS ACTUAL — YTD 2026
Account_Number | Account_Name | Budget_YTD | Actual_YTD | Variance | Variance_% | Status
4000 | Wholesale Assignment Fees | 25000 | 0 | 25000 | 100% | UNDER BUDGET
5100 | Rehab — Labor | 26000 | 8000 | 18000 | 69.23% | UNDER BUDGET
5110 | Rehab — Materials | 16000 | 3500 | 12500 | 78.12% | UNDER BUDGET
5210 | Holding — Mortgage | 3750 | 750 | 3000 | 80% | UNDER BUDGET
6100 | Marketing — Digital | 7500 | 0 | 7500 | 100% | UNDER BUDGET
6120 | Marketing — Software | 1495 | 299 | 1196 | 80% | UNDER BUDGET
6300 | Professional Fees — Legal | 1500 | 0 | 1500 | 100% | UNDER BUDGET
6310 | Professional Fees — Accounting | 1250 | 0 | 1250 | 100% | UNDER BUDGET

## 20_BANK_ACCOUNTS
BANK ACCOUNTS REGISTRY
Account_ID | Bank_Name | Account_Type | Account_Number | Routing_Number | Opening_Balance | Current_Balance | Last_Reconciled | Status | Notes
BA001 | Chase Bank | Business Checking | XXXX-1234 | 021000021 | 0 | 17200 | 05/29/2026 | Active | Primary operating account
BA002 | Chase Bank | Business Savings | XXXX-5678 | 021000021 | 0 | 0 |  | Active | Reserve fund

## 21_BANK_TRANSACTIONS
BANK TRANSACTIONS FEED
Trans_ID | Date | Account_ID | Description | Amount | Trans_Type | Category | GL_Account | Matched | Reconciled | Reference | Notes
BT001 | 05/01/2026 | BA001 | Capital contribution | 25000 | Deposit | Capital | 3030 | Yes | Yes | WIRE-001 | Opening capital
BT002 | 05/01/2026 | BA001 | 502 Buckley closing costs | -4500 | Withdrawal | Acquisition | 5010 | Yes | Yes | CHECK-001
BT003 | 05/15/2026 | BA001 | Demo materials | -3500 | Withdrawal | Rehab | 5110 | Yes | Yes | CHECK-002
BT004 | 05/25/2026 | BA001 | PropWire subscription | -299 | Withdrawal | Marketing | 6120 | Yes | Yes | CC-001
BT005 | 05/29/2026 | BA001 | Misc income | 500 | Deposit | Other | 4400 | No | No |  | Pending match

## 22_RECONCILIATION
BANK RECONCILIATION — Chase Business Checking — May 2026
BANK STATEMENT SECTION
Bank Statement Balance | 17200
+ Deposits in Transit | 0
- Outstanding Checks | 0
ADJUSTED BANK BALANCE | 17200
BOOK (GL) SECTION
Book Balance (per GL) | 17201
+ Interest Earned | 0
- Bank Charges | 0
ADJUSTED BOOK BALANCE | 17201
DIFFERENCE (must = $0) | -1

## 23_CREDIT_CARDS
CREDIT CARD TRANSACTIONS
Trans_ID | Date | Card_Name | Merchant | Amount | Category | GL_Account | Entity | Reimbursable | Reconciled | Notes
CC001 | 05/25/2026 | Chase Business | PropWire | 299 | Marketing Software | 6120 | STLLC | No | No | Monthly sub
CC002 | 05/20/2026 | Chase Business | Home Depot | 450 | Rehab Materials | 5110 | STLLC | No | No | Demo supplies

## 30_CUSTOMERS
CUSTOMER DATABASE
Customer_ID | First_Name | Last_Name | Company | Email | Phone | Address | Customer_Type | Credit_Limit | Outstanding_Balance | Status | Notes
C001 | John | Smith |  | john@email.com | 314-555-0001 | St. Louis, MO | Buyer | 500000 | 0 | Active | Cash buyer — wholesale deals
C002 | Mary | Johnson |  | mary@email.com | 314-555-0002 | St. Louis, MO | Tenant | 2000 | 0 | Active | Potential tenant — 502 Buckley

## 31_INVOICES
INVOICE MANAGEMENT
Invoice_ID | Date | Customer_ID | Customer_Name | Property | Description | Amount | Tax | Total | Due_Date | Status | GL_Account | Entity | Notes
INV-001 | 05/29/2026 | C001 | John Smith |  | Assignment Fee — 123 Main St | 15000 | 0 | 15000 | 06/15/2026 | Pending | 4000 | STLLC

## 32_RECEIVABLES
ACCOUNTS RECEIVABLE TRACKER
AR_ID | Invoice_ID | Customer_ID | Customer_Name | Original_Amount | Amount_Paid | Balance_Due | Invoice_Date | Due_Date | Days_Outstanding | Status
AR001 | INV-001 | C001 | John Smith | 15000 | 0 | 15000 | 05/29/2026 | 06/15/2026 | 0 | Pending
Formulas:
Days_Outstanding = IF([Status]="Paid",0,MAX(0,TODAY()-[Due_Date]))

## 33_AGING_REPORT
ACCOUNTS RECEIVABLE AGING — As of Today
Customer_Name | Current | 1-30 Days | 31-60 Days | 61-90 Days | 90+ Days | Total
John Smith | 15000 | 0 | 0 | 0 | 0 | 15000
TOTAL | 15000 | 0 | 0 | 0 | 0 | 15000

## 40_VENDORS
VENDOR DATABASE
Vendor_ID | Vendor_Name | Contact_Name | Email | Phone | Address | Vendor_Type | Payment_Terms | W9_On_File | 1099_Required | Outstanding_Balance | Status | Notes
V001 | General Contractor | TBD |  | 314-555-0100 | St. Louis, MO | Contractor | Net 30 | Yes | Yes | 8000 | Active | Primary rehab contractor
V002 | PropWire |  | billing@propwire.com |  |  | Software | Monthly | No | No | 0 | Active | Lead generation software
V003 | Home Depot |  |  |  |  | Supplier | Net 0 | No | No | 450 | Active | Materials supplier

## 41_BILLS
BILL MANAGEMENT — Accounts Payable
Bill_ID | Date | Vendor_ID | Vendor_Name | Description | Amount | Due_Date | Status | GL_Account | Property | Entity | Approved_By | Notes
BILL-001 | 05/20/2026 | V001 | General Contractor | Labor — Demo phase 502 Buckley | 8000 | 06/20/2026 | Unpaid | 5100 | 502 Buckley | STLLC | Shylow | Phase 1 labor
BILL-002 | 05/25/2026 | V002 | PropWire | Monthly subscription | 299 | 06/01/2026 | Paid | 6120 |  | STLLC | Shylow
BILL-003 | 05/20/2026 | V003 | Home Depot | Demo supplies | 450 | 05/20/2026 | Paid | 5110 | 502 Buckley | STLLC | Shylow

## 42_PAYABLES
ACCOUNTS PAYABLE TRACKER
AP_ID | Bill_ID | Vendor_ID | Vendor_Name | Original_Amount | Amount_Paid | Balance_Due | Bill_Date | Due_Date | Days_Outstanding | Status
AP001 | BILL-001 | V001 | General Contractor | 8000 | 0 | 8000 | 05/20/2026 | 06/20/2026 | 0 | Unpaid
AP002 | BILL-002 | V002 | PropWire | 299 | 299 | 0 | 05/25/2026 | 06/01/2026 | 0 | Paid
AP003 | BILL-003 | V003 | Home Depot | 450 | 450 | 0 | 05/20/2026 | 05/20/2026 | 0 | Paid
Formulas:
Days_Outstanding = IF([Status]="Paid",0,MAX(0,TODAY()-[Due_Date]))

## 43_AGING_PAYABLES
ACCOUNTS PAYABLE AGING — As of Today
Vendor_Name | Current | 1-30 Days | 31-60 Days | 61-90 Days | 90+ Days | Total
General Contractor | 8000 | 0 | 0 | 0 | 0 | 8000
PropWire | 0 | 0 | 0 | 0 | 0 | 0
Home Depot | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 8000 | 0 | 0 | 0 | 0 | 8000

## 50_PROPERTY_MASTER
PROPERTY MASTER — Real Estate Portfolio
Property_ID | Address | City | State | Zip | Property_Type | Status | Purchase_Date | Purchase_Price | Land_Value | Building_Value | Closing_Costs | ARV | Rehab_Budget | Rehab_Actual | Rehab_Variance | Loan_Balance | Loan_Type | Monthly_Payment | Monthly_Rent | NOI | DSCR | Cap_Rate | Equity | Exit_Strategy
P001 | 502 Buckley | St. Louis | MO | 63137 | Single Family | Active — Rehab | 05/01/2026 | 114000 | 16100 | 97900 | 4500 | 200000 | 90000 | 11500 | 78500 | 114000 | FHA | 750 | 0 | 0 | 0 | 0% | 86000 | BRRR
Notes: | 502 Buckley objectives: Fix crawlspace/floor issues, add basement, add 3rd bedroom. FHA purchase 05/01/2026. Rehab in progress.

## 51_ACQUISITIONS
ACQUISITIONS — Deal Pipeline
Acq_ID | Property | Address | Lead_Source | Lead_Date | Contract_Date | Purchase_Price | ARV | Rehab_Est | MAO | Spread | Under_Contract | Closing_Date | Entity | Deal_Type | Status | Notes
ACQ001 | 502 Buckley | 502 Buckley, St. Louis MO 63137 | Direct | 04/15/2026 | 04/25/2026 | 114000 | 200000 | 90000 | 50000 | -64000 | Yes | 05/01/2026 | STLLC | BRRR | Closed | FHA purchase. Rehab in progress. Objectives: crawlspace, basement, 3rd bedroom

## 52_REHAB_ENGINE
REHAB BUDGET & TRACKER — 502 Buckley St. Louis MO
Work_Order | Category | Scope_of_Work | Budget | Actual | Variance | Pct_Complete | Status | Contractor | Start_Date | End_Date | Notes
WO001 | Demo & Site Prep | Clear structure, remove debris, dumpsters | 5000 | 3500 | 1500 | 7000% | In Progress | TBD | 05/10/2026 | 05/31/2026 | Phase 1
WO002 | Crawlspace/Foundation | Fix crawlspace, address foundation issues, add drainage | 12000 | 0 | 12000 | 0% | Pending | TBD |  |  | Critical — must complete first
WO003 | Basement Addition | Excavate and pour basement, waterproof | 20000 | 0 | 20000 | 0% | Pending | TBD |  |  | Major addition
WO004 | Framing | Add 3rd bedroom framing, structural repairs | 8000 | 0 | 8000 | 0% | Pending | TBD
WO005 | Roofing | Full roof replacement | 6000 | 0 | 6000 | 0% | Pending | TBD
WO006 | Exterior/Siding | Siding, exterior paint, gutters | 4000 | 0 | 4000 | 0% | Pending | TBD
WO007 | Windows & Doors | Replace all windows and exterior doors | 5000 | 0 | 5000 | 0% | Pending | TBD
WO008 | Electrical | Full electrical upgrade, 200 amp panel | 8000 | 0 | 8000 | 0% | Pending | TBD
WO009 | Plumbing | Rough plumbing, fixtures, water heater | 6000 | 0 | 6000 | 0% | Pending | TBD
WO010 | HVAC | New forced air system, ductwork | 7000 | 0 | 7000 | 0% | Pending | TBD
WO011 | Insulation | Full house insulation | 2500 | 0 | 2500 | 0% | Pending | TBD
WO012 | Drywall | Hang, tape, mud, sand throughout | 4000 | 0 | 4000 | 0% | Pending | TBD
WO013 | Interior Doors | All interior doors and hardware | 1500 | 0 | 1500 | 0% | Pending | TBD
WO014 | Flooring | LVP main floor, carpet bedrooms | 5000 | 0 | 5000 | 0% | Pending | TBD
WO015 | Kitchen | Full kitchen — cabinets, counters, backsplash | 8000 | 0 | 8000 | 0% | Pending | TBD
WO016 | Bathroom 1 | Full master bath renovate | 4000 | 0 | 4000 | 0% | Pending | TBD
WO017 | Bathroom 2 | Second bathroom add or renovate | 3500 | 0 | 3500 | 0% | Pending | TBD
WO018 | Paint — Interior | Full interior prime + 2 coats | 2500 | 0 | 2500 | 0% | Pending | TBD
WO019 | Paint — Exterior | Exterior paint and trim | 1500 | 0 | 1500 | 0% | Pending | TBD
WO020 | Cabinets/Millwork | Built-ins, closets, trim | 2000 | 0 | 2000 | 0% | Pending | TBD
WO021 | Landscaping | Grading, seed, basic curb appeal | 1500 | 0 | 1500 | 0% | Pending | TBD
WO022 | Driveway/Parking | Concrete or asphalt driveway | 2500 | 0 | 2500 | 0% | Pending | TBD
WO023 | Appliances | Range, fridge, dishwasher, W/D hook | 3000 | 0 | 3000 | 0% | Pending | TBD
WO024 | Lighting/Fixtures | All lighting, ceiling fans, switches | 2000 | 0 | 2000 | 0% | Pending | TBD
WO025 | Cleanup/Final | Final debris removal, touch-ups | 1000 | 0 | 1000 | 0% | Pending | TBD
WO026 | Permits | All building permits | 1500 | 0 | 1500 | 0% | Pending | TBD
WO027 | Inspections | All required inspections | 500 | 0 | 500 | 0% | Pending | TBD
WO028 | Contingency 10% | 10% contingency reserve | 12750 | 0 | 12750
WO029 | GC Overhead 10% | General contractor markup | 12750 | 0 | 12750
WO030 | Change Orders | Approved change orders | 0 | 8000 | -8000
TOTAL REHAB BUDGET |  |  | 153000 | 11500 | 141500
REHAB HEALTH SCORE: |  |  | GREEN — ON TRACK

## 53_DRAWS
CONSTRUCTION DRAW SCHEDULE
Draw_ID | Date | Property | Lender | Draw_Amount | Draw_Purpose | Work_Completed_% | Inspector_Approved | Funded | Draw_Number | Cumulative_Draws | Remaining_Budget | Notes
DR001 | 05/15/2026 | 502 Buckley | FHA/Personal | 3500 | Demo phase materials — lumber, dumpster | 70 | No | Yes | 1 | 3500 | 86500 | Initial materials draw

## 54_HOLDING_COSTS
HOLDING COSTS TRACKER
HC_ID | Property | Month | Mortgage | Property_Tax | Insurance | Utilities | HOA | Other | Total_Monthly | Cumulative_Total | Notes
HC001 | 502 Buckley | May 2026 | 750 | 150 | 100 | 80 | 0 | 0 | 1080 | 1080

## 55_RENTS
RENT ROLL — Rental Income Tracker
Rent_ID | Property | Unit | Tenant_Name | Lease_Start | Lease_End | Monthly_Rent | Security_Deposit | Deposit_Held | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Annual_Rent | Collected_YTD | Notes
RENT001 | 502 Buckley | Unit 1 | VACANT |  |  | 1400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending rehab completion — est. rental ready Q4 2026

## 56_CAPEX
CAPITAL EXPENDITURES — Asset Register
CapEx_ID | Date | Property | Description | Amount | Asset_Class | Useful_Life | Annual_Depreciation | Accumulated_Depr | Book_Value | Capitalized | Notes
CE001 | 05/01/2026 | 502 Buckley | Building purchase | 97900 | Residential RE | 27.5 | 3560 | 0 | 97900 | Yes | FHA purchase allocation
CE002 | 05/01/2026 | 502 Buckley | Land purchase | 16100 | Land | 0 | 0 | 0 | 16100 | Yes | Land not depreciated

## 57_DISPOSITIONS
DISPOSITIONS — Property Sales Log
Disp_ID | Property | Sale_Date | Sale_Price | Purchase_Price | Rehab_Cost | Holding_Costs | Selling_Costs | Total_Costs | Net_Profit | ROI | Annualized_ROI | Hold_Days | Exit_Type | Buyer | Notes
[No dispositions yet]

## 60_WHOLESALE_ANALYZER
WHOLESALE DEAL ANALYZER — Dynasty Accounting OS
INPUTS (Blue = Editable)
Property Address |  |  | [ENTER ADDRESS]
ARV (After Repair Value) |  |  | 150000
Purchase Price |  |  | 60000
Assignment Fee Target |  |  | 15000
Marketing Cost |  |  | 2000
Inspection Cost |  |  | 500
Other Costs |  |  | 300
CALCULATIONS
MAO (70% Rule) |  |  | 105000
Max Purchase Price |  |  | 97500
Gross Spread |  |  | 90000
Total Costs |  |  | 2800
Net Assignment Fee |  |  | 12200
ROI on Marketing |  |  | 435.7%
DECISION |  |  | GO — DEAL WORKS
WHOLESALE PIPELINE
Lead | Status | ARV | Asking | Offer | Assignment_Fee | Mktg_Cost | Net_Profit | Decision

## 61_FLIP_ANALYZER
FIX & FLIP ANALYZER — 502 Buckley Analysis
INPUTS — 502 Buckley, St. Louis MO
Property Address | 502 Buckley, St. Louis MO 63137
Purchase Price | 114000
Closing Costs — Purchase | 4500
Rehab Budget | 90000
Holding Period (months) | 9
Monthly Holding Cost | 1080
Selling Price (ARV) | 200000
Realtor Commission % | 6%
Closing Costs Sale % | 3%
Other Selling Costs | 2000
FLIP ANALYSIS
Total Acquisition Cost | 118500
Total Rehab Cost | 90000
Total Holding Costs | 9720
Total Selling Costs | 20000
TOTAL PROJECT COST | 238220
NET PROFIT | -38220
ROI | -16.04%
Annualized ROI | -20.8%
DECISION | DO NOT FLIP

## 62_BRRR_ANALYZER
BRRR ANALYZER — Buy, Rehab, Rent, Refinance, Repeat
INPUTS — 502 Buckley BRRR Analysis
Purchase Price | 114000
Closing Costs | 4500
Rehab Cost | 90000
ARV After Rehab | 200000
Monthly Rent | 1400
Vacancy Rate % | 5%
Operating Expense % | 35%
Refinance LTV % | 75%
Refinance Interest Rate % | 7%
Refinance Term (years) | 30
Total Holding Costs During Rehab | 9720
BRRR ANALYSIS
Total Investment (All-In) | 218220
Refinance Amount | 150000
Monthly Mortgage (Refi) | 997.9537
Effective Monthly Rent | 1330
Monthly Operating Expenses | 465.5
Monthly NOI | 864.5
Monthly Cash Flow | -133.4537
Annual Cash Flow | -1601.4449
Cash Left in Deal | 68220
Cash-on-Cash Return | -0.023475
Cap Rate | 5.187%
DSCR | 0.86627
Equity Created | -8500
Cash Recovered | -58500
DECISION | DSCR TOO LOW — RENEGOTIATE

## 63_DEVELOPMENT_ANALYZER
DEVELOPMENT DEAL ANALYZER
INPUTS
Land Cost | 0
Soft Costs (permits, arch, eng) | 0
Hard Construction Costs | 0
Financing Costs | 0
Contingency % | 10%
Number of Units | 1
Projected Sale Price per Unit | 0
DEVELOPMENT ANALYSIS
Base Development Cost | 0
Contingency Reserve | 0
TOTAL DEVELOPMENT COST | 0
Cost Per Unit | 0
Gross Development Value (GDV) | 0
Development Profit | 0
Development Margin | 0%
ROI | 0%
DECISION | NOT VIABLE

## 64_LAND_ANALYZER
LAND DEAL ANALYZER
INPUTS
Purchase Price | 0
Entitlement Costs | 0
Carrying Costs / Month | 0
Hold Period (months) | 12
Target Sale Price | 0
Assignment Fee Option | 0
LAND ANALYSIS
Total Carrying Costs | 0
Total Cost (Hold) | 0
Net Profit (Sell) | 0
ROI (Sell) | 0%
Net Profit (Assign) | 0
ROI (Assign) | 0%
Annualized ROI | 0%

## 70_INVESTORS
INVESTOR REGISTRY — Dynasty Accounting OS
Investor_ID | Full_Name | Entity | Email | Phone | Accredited | Capital_Committed | Capital_Called | Capital_Returned | Pref_Return_% | Profit_Split_% | Current_Balance | Status | Notes
INV001 | Private Lender 1 | [TBD] |  |  | Yes | 50000 | 0 | 0 | 8% | 30% | 0 | Active | Hard money / private lender potential

## 71_CAPITAL_STACK
CAPITAL STACK — 502 Buckley
Tranche | Source | Type | Amount | Rate_% | Term | LTV_% | Position | Monthly_Payment | Total_Cost | Notes
Senior Debt | FHA Mortgage | Debt | 114000 | 6.5% | 30 years | 57% | 1st Lien | 750 | 270000 | FHA purchase loan at 6.5%
Equity | Owner Capital | Equity | 18500 | 0% | N/A | N/A | Equity | 0 | N/A | Owner equity + closing costs
TOTALS |  |  | 132500 |  |  |  |  | 750

## 72_WATERFALL
DISTRIBUTION WATERFALL — 3-Tier Structure
WATERFALL INPUTS
Total Distributions Available | 0
Total Investor Capital Invested | 50000
Preferred Return Rate % | 8%
Investor Profit Share % | 30%
Owner Profit Share % | 70%
WATERFALL DISTRIBUTION
TIER 1: Return of Capital | 0
Remaining After Tier 1 | 0
TIER 2: Preferred Return (8% annualized) | 0
Remaining After Tier 2 | 0
TIER 3: Investor Profit Share (30%) | 0
Owner Profit Share (70%) | 0
INVESTOR TOTAL | 0
OWNER TOTAL | 0
GRAND TOTAL CHECK | 0

## 73_DISTRIBUTIONS
DISTRIBUTION HISTORY
Dist_ID | Date | Property_Fund | Investor_ID | Investor_Name | Dist_Type | Amount | ROC | Preferred | Profit | Cumulative | Notes
[No distributions yet]

## 74_INVESTOR_REPORTS
INVESTOR SUMMARY REPORT — Dynasty Accounting OS
Report Date: 05/29/2026 ¦ Prepared by: Dynasty Accounting OS v1.0
Investor_ID | Name | Capital_Invested | Distributions | Current_Balance | Pref_Return_Earned | IRR | Status
INV001 | Private Lender 1 | 50000 | 0 | 50000 | 0 | N/A | Active

## 80_AI_DEAL_SCORING
AI DEAL SCORING ENGINE — TROOPER_ACCOUNTANT
STATUS: Placeholder formulas active ¦ Connect AI API for enhanced ML scoring ¦ All scores calculated via weighted formula matrix
Deal_ID | Address | Deal_Type | ARV | Purchase | Rehab | Spread | Margin_% | DSCR | Cash_Flow | Score | Grade | AI_Recommendation
DEAL001 | 502 Buckley, St. Louis MO | BRRR | 200000 | 114000 | 90000 | 86000 | -2% | 0 | 0 | 0 | D | AVOID

## 81_AI_FORECASTING
13-WEEK ROLLING CASH FORECAST — Dynasty Accounting OS
Week | Week_Start | Week_End | Beginning_Balance | Expected_Inflows | Expected_Outflows | Net_Change | Ending_Balance | Alert
1 | 05/29/2026 | 06/04/2026 | 17200 | 0 | 3800 | -3800 | 13400 | WARNING — MONITOR
2 | 06/05/2026 | 06/11/2026 | 13400 | 0 | 1500 | -1500 | 11900 | WARNING — MONITOR
3 | 06/12/2026 | 06/18/2026 | 11900 | 5000 | 8500 | -3500 | 8400 | WARNING — MONITOR
4 | 06/19/2026 | 06/25/2026 | 8400 | 5000 | 1500 | 3500 | 11900 | WARNING — MONITOR
5 | 06/26/2026 | 07/02/2026 | 11900 | 5000 | 8500 | -3500 | 8400 | WARNING — MONITOR
6 | 07/03/2026 | 07/09/2026 | 8400 | 5000 | 1500 | 3500 | 11900 | WARNING — MONITOR
7 | 07/10/2026 | 07/16/2026 | 11900 | 5000 | 8500 | -3500 | 8400 | WARNING — MONITOR
8 | 07/17/2026 | 07/23/2026 | 8400 | 5000 | 1500 | 3500 | 11900 | WARNING — MONITOR
9 | 07/24/2026 | 07/30/2026 | 11900 | 5000 | 8500 | -3500 | 8400 | WARNING — MONITOR
10 | 07/31/2026 | 08/06/2026 | 8400 | 5000 | 1500 | 3500 | 11900 | WARNING — MONITOR
11 | 08/07/2026 | 08/13/2026 | 11900 | 5000 | 3800 | 1200 | 13100 | WARNING — MONITOR
12 | 08/14/2026 | 08/20/2026 | 13100 | 5000 | 1500 | 3500 | 16600 | OK
13 | 08/21/2026 | 08/27/2026 | 16600 | 5000 | 1500 | 3500 | 20100 | OK

## 82_AI_ANOMALIES
AI ANOMALY DETECTION — Expense Monitor
STATUS: Monitoring active ¦ Connect to live transaction feed for real-time anomaly detection ¦ Threshold: >50% variance from average
Detection_Date | Account | Category | Amount | Avg_Amount | Variance_% | Anomaly_Flag | Severity | Notes
05/25/2026 | 6120 | Marketing Software | 299 | 299 | 0% | Normal | LOW
05/20/2026 | 5110 | Rehab Materials | 3500 | 3500 | 0% | Normal | LOW

## 83_AI_ASSISTANT
AI ACCOUNTING ASSISTANT — TROOPER_ACCOUNTANT
TROOPER_ACCOUNTANT ¦ Institutional-grade AI accounting assistant for Dynasty Accounting OS
CAPABILITY |  |  | DESCRIPTION
Auto-categorize transactions |  |  | Connect to bank feed API — auto-matches transactions to COA
Detect expense anomalies |  |  | Flags variances >50% from historical average per category
Forecast 13-week cash flow |  |  | Uses budget + AR/AP aging to project weekly cash position
Analyze property performance |  |  | Calculates ROI, DSCR, Cap Rate, Cash-on-Cash for all properties
Score deals (0-100) |  |  | Weighted scoring: margin 40%, DSCR 30%, cash flow 30%
Prepare lender packages |  |  | Generates formatted lender-ready financial summaries
Prepare investor reports |  |  | Generates distribution statements and portfolio reports
Monitor KPI drift |  |  | Alerts when KPIs deviate >10% from targets
Generate financial narratives |  |  | Creates plain-English summaries of financial performance
Simulate scenarios |  |  | Models best/base/worst case scenarios for each property
API INTEGRATION CONFIGURATION
Function | Status | API_Endpoint | Last_Run | Notes
Transaction Categorization | PLACEHOLDER — Configure API endpoint
Anomaly Detection | PLACEHOLDER — Configure API endpoint
Cash Forecasting | PLACEHOLDER — Configure API endpoint
Deal Scoring | PLACEHOLDER — Configure API endpoint
Report Generation | PLACEHOLDER — Configure API endpoint

## 90_KPI_DASHBOARD
DYNASTY ACCOUNTING OS — KPI COMMAND CENTER
CASH & FINANCIAL METRICS
CASH AVAILABLE | MONTHLY REVENUE | MONTHLY EXPENSES | NET INCOME MTD
17200 | 0 | 11799 | -11799
Bank balance | MTD revenue | MTD expenses | Revenue - Expenses
REAL ESTATE PORTFOLIO METRICS
ACTIVE PROPERTIES | PORTFOLIO ARV | PORTFOLIO EQUITY | REHAB IN PROGRESS
1 | 200000 | 86000 | 1
Count | Total ARV | ARV - Debt | Properties
OBLIGATIONS & PIPELINE
TOTAL DEBT | MONTHLY DEBT SERVICE | AP BALANCE | AR BALANCE
114000 | 750 | 8000 | 15000
Mortgages + loans | All loan payments | Total owed to vendors | Total owed to company
DEAL PIPELINE
WHOLESALE PIPELINE | FLIP PIPELINE | BRRR PIPELINE | MTD ASSIGN FEES
$0 | $114K | $114K | $0
Active deals | 502 Buckley | 502 Buckley | This month

## 91_CASH_FORECAST
12-MONTH CASH FORECAST — FY 2026
Month | Beginning_Balance | Revenue | Expenses | Net_Change | Ending_Balance | Notes
Jan 2026 | 0 | 0 | 0 | 0 | 0 | Rehab in progress
Feb 2026 | 0 | 0 | 0 | 0 | 0 | Rehab in progress
Mar 2026 | 0 | 0 | 0 | 0 | 0 | Rehab in progress
Apr 2026 | 0 | 0 | 0 | 0 | 0 | Rehab in progress
May 2026 | 0 | 500 | 11799 | -11299 | -11299 | Rehab in progress
Jun 2026 | -11299 | 5000 | 11799 | -6799 | -18098 | Est. wholesale activity
Jul 2026 | -18098 | 5000 | 11799 | -6799 | -24897 | Est. wholesale activity
Aug 2026 | -24897 | 5000 | 5000 | 0 | -24897 | Est. wholesale activity
Sep 2026 | -24897 | 5000 | 5000 | 0 | -24897 | Est. wholesale activity
Oct 2026 | -24897 | 10000 | 5000 | 5000 | -19897 | Projected
Nov 2026 | -19897 | 10000 | 5000 | 5000 | -14897 | Projected
Dec 2026 | -14897 | 10000 | 5000 | 5000 | -9897 | Projected

## 92_NET_WORTH_TRACKER
NET WORTH TRACKER — Shylow Thompson LLC
Date | Cash_Total | Property_Values | Other_Assets | Total_Assets | Total_Liabilities | Net_Worth | Change | Notes
05/29/2026 | 17200 | 200000 | 0 | 217200 | 122299 | 94901 | 0 | Inception — Dynasty Accounting OS v1.0

## 93_PORTFOLIO_ANALYTICS
PORTFOLIO ANALYTICS — Dynasty Accounting OS
PROPERTY PERFORMANCE TABLE
Property | Purchase | ARV | Equity | NOI | DSCR | Cap_Rate | Cash_Flow | Status | Grade
502 Buckley | 114000 | 200000 | -28000 | 0 | 0 | 0% | 0 | Active — Rehab | B
REVENUE MIX (YTD)
Wholesale Assignment Fees | 0
Flip Profits | 0
Rental Income | 0
Consulting/Other | 500
TOTAL REVENUE YTD | 500
PORTFOLIO KPIs
Total Properties | 1
Total Portfolio ARV | $200,000
Total Debt | $114,000
Total Equity | $86,000
Avg Cap Rate | 0.0%
Portfolio DSCR | 0.00x

## 94_EXECUTIVE_REPORT
DYNASTY ACCOUNTING OS — EXECUTIVE SUMMARY REPORT
Shylow Thompson LLC ¦ Period: YTD 2026 ¦ Generated: 05/29/2026 ¦ Dynasty Accounting OS v1.0
1. COMPANY OVERVIEW
Entity | Shylow Thompson LLC — Real Estate Investment Company
State | Missouri
Business Lines | Wholesale, BRRR, Flip, Development, Rentals
Accounting System | Dynasty Accounting OS v1.0 — Accrual Basis
Reporting Period | January 1, 2026 — May 29, 2026
2. FINANCIAL HIGHLIGHTS
Total Revenue YTD | $500
Total Expenses YTD | $11,799
Net Income YTD | ($11,299)
Cash Position | $17,200
Note | Net loss reflects startup + rehab investment phase — expected
3. BALANCE SHEET SUMMARY
Total Assets | $217,200
Total Liabilities | $122,299
Net Worth / Equity | $94,901
Primary Asset | 502 Buckley — ARV $200,000
4. REAL ESTATE PORTFOLIO
Active Properties | 1 — 502 Buckley, St. Louis MO 63137
Status | Active Rehabilitation
Purchase Price | $114,000
Rehab Budget | $90,000
Rehab Actual | $11,500 (12.8% complete)
Estimated ARV | $200,000
Exit Strategy | BRRR — Refinance + Hold as Rental
5. KEY RISKS & OPPORTUNITIES
Risk 1 | Rehab cost overruns — monitor weekly vs 90K budget
Risk 2 | Cash position — 17K available vs 90K rehab remaining
Opportunity 1 | 502 Buckley BRRR — est. $86K equity creation
Opportunity 2 | Wholesale pipeline — 0 active deals, needs marketing
6. 90-DAY OUTLOOK
Rehab Completion Target | August 2026 (est.)
Estimated Cash Need | $78,500 additional rehab funding
Revenue Opportunity | $10,000-$25,000 wholesale deals
Next Action | Secure rehab financing / private lender capital
DISCLAIMER: This report is for internal management use only. Generated by Dynasty Accounting OS v1.0 ¦ Shylow Thompson LLC Confidential